Excerpts from Iowa’s SIG Application

Part I – Section D, # 4: Describe how the SEA will monitor each LEA that receives a School Improvement Grant to ensure that it is implementing a school intervention model fully and effectively in the Tier I and Tier II schools the LEA is approved to serve.

- Members of the Iowa State School Support Team will be assigned to each LEA receiving School Improvement Grant funds to conduct onsite visits once a semester to each LEA. The purpose of the onsite visit will be to document LEA and school progress in implementing the intervention model and associated actions according to the established timeline and whether any deficiencies exist in LEA and school commitment and support. The outcome of an onsite visit will be the submission of a Technical Assistance Report to the Title I administrative consultant who will review the findings and determine whether any follow up actions need to be taken.

- Each LEA receiving School Improvement Grant funds will be required to submit an annual report that (1) documents progress on the annual goals for each school, (2) describes the extent to which the intervention model and associated actions for each school have been implemented. and (3) identifies any remedial actions that will be taken to correct deficiencies in implementation. The annual report and Technical Assistance Reports will be reviewed by a team of Department personnel to determine whether any specific follow up actions need to be taken with an LEA and its school(s).

Part I – Section F: The SEA must briefly describe the activities related to administration, evaluation, and technical assistance that the SEA plans to conduct with the State-level funds it has received from its School Improvement Grant.

The Iowa Department of Education (1DE) will reserve an amount equal to five percent if its School Improvement Grant to conduct the following activities:

- Review and approve LEA School Improvement Grant applications.

- Monitor of LEA implementation of approved applications.

- Ensure that LEAs implement one of the four intervention models in each Tier I and Tier II schools that it commits to serve.

- Ensure that school improvement activities are implemented in each Tier 111 school that an approved LEA commits to serve with School Improvement Grant funds.

- Review school level reports on student achievement and leading indicators.

- Provide technical assistance on the implementation of required components in the model selected by each school that the LEA commits to serve.

- Assist in providing student achievement information and analysis from to LEAs.

- Provide research and professional development on effective interventions and instructional models to LEAs through the use of the State Support Team.

- Evaluate data submitted and use of data to provide technical assistance.