Excerpts from Missouri’s SIG Application

Part I – Section D, # 4: Describe how the SEA will monitor each LEA that receives a School Improvement Grant to ensure that it is implementing a school intervention model fully and effectively in the Tier I and Tier II schools the LEA is approved to serve.

Department staff and /or designated support team staff will meet quarterly with LEA/district-level staff and school principals responsible for the intervention and improvement activities. The LEA/district will provide documentation of implementation measures and leading indicator measures for each school served. Department staff and /or designated support team staff will make not less than one school visit each month to monitor implementation. The school visits will include classroom observations and staff, student, and parent interviews.

Monitoring will include evaluation of:

- The LEA/district and school fidelity to the implementation of the planned interventions and improvement activities

- Implementation measures and timelines

- Leading indicators as required by the SIG Regulations and those identified by the

- LEA/district and school

- Department Financial and Grants Management staff will monitor the budgetary aspects of the grant implementation quarterly

- Annually Department Financial and Grants Management and Federal Instructional

- Improvement Sections will monitor LEAs that are receiving SIG funds using selected parts of the Department’s Self-Monitoring Checklist which can be found at: http://dese.mo.gov/divimprove/fedprog/documents/MO5002336.pdf. Areas monitored will include but not be limited to:

LEA/district and school improvement plans

  - Obligation of funds

  - Accounting requirements

  - Staff paid with federal funds

  - Supplement, not supplant

  - Annual evaluation process

  - Parent involvement

  - Budget and expenditure reports

Part I – Section F: The SEA must briefly describe the activities related to administration, evaluation, and technical assistance that the SEA plans to conduct with the State-level funds it has received from its School Improvement Grant.

The Department will use the SEA reservations to fund:

- collaborative Department/LEA/district planning activities,

- Department support for LEAs/districts as they develop their applications, and

- Department support for LEAs/districts as they implement the selected interventions and improvement activities

- Department monitoring and evaluation of LEA/district SIG activities

- Department administrative activities related to the SIG program

In addition the Department will seek outside partners and/or build capacity within the Department to provide support to LEAs/Districts during the planning, application process, implementation, and evaluation of SIG activities. Scope of work for the Department and its partner(s) may include but not be limited to:

- Advising/consulting with the Department on selecting data to provide meaningful feedback to LEAs and schools

- Performing a needs analysis of the district and school to assist in

  - coordinating with all involved stakeholders on the development of an intervention plan and its implementation; and

  - implementing a coherent, whole-school intervention model in partnership

- Developing a fair and consistent method to evaluate the effectiveness of the existing principal and determine whether the principal can serve as the instructional leader for the intervention.

- Providing frequent progress assessments and demonstrating an adaptability to changing program needs

- Demonstrating ongoing, significant progress while building district capacity to implement and sustain activities aligned with improving student outcomes

- Providing formative and ongoing reports on program effectiveness to include, but not limited to, student achievement, parental involvement, student attendance, and student discipline

- Employing research-based strategies that provide an immediate and dramatic turnaround in student achievement

- Working with the LEA to recruit and recommend teachers and a leader(s) who have a proven record of success of increasing student achievement and assistance in implementing intensive induction and mentoring support for teachers

- Promoting parental capacity to support student engagement, motivation, and learning within school, at home and in the community

- Working with the LEA to expand community support to garner human resources needed for reform

- Evaluating teacher and leader performance and outcomes and make staffing recommendations accordingly

- Recommending changes to the school calendar according to student and program needs, for example, year-round schools or extending the length of the school day and working with the school division to obtain a commitment from teachers to allow for additional time for instruction and professional development.

- Providing comprehensive, coherent, manageable and integrated instructional and support programs.

- Recommending which existing programs are to be continued and which programs are to be eliminated.

- Recommending alignment of curriculum, instruction, classroom formative assessment and sustained professional development to build rigor, foster student-teacher relationships, and provide relevant instruction that engages and motivates students.

- Identifying and recommending supporting partners to address social, emotional and behavioral issues to provide a braided system of support… wrap-around services for low-income students so educators can focus on teaching and learning while ensuring students’ social, emotional, and physical needs are met.

- Building capacity within the local school board to oversee and implement Missouri’s Turnaround Model

- Building the capacity of district superintendents, assistant superintendents, human resource directors, and/or fiscal officers to oversee and implement Missouri’s Turnaround Model

- Using data to identify and implement comprehensive, research-based, instructional programs that include:

  - development and use of frequent formative assessments permitting rapid-time analysis, feedback, and targeted instruction;

  - other data-driven instructional systems and strategies.