Excerpts from New Jersey’s SIG Application

Part I – Section D, # 4: Describe how the SEA will monitor each LEA that receives a School Improvement Grant to ensure that it is implementing a school intervention model fully and effectively in the Tier I and Tier II schools the LEA is approved to serve.

The NJDOE requires quarterly fiscal and program reports as outlined in the NGO, Section 1.9.  The specifics of the NJDOE oversight are in the NGO, Section 1.10. Details of the State required activities are in Section 2.2.

Notice of Grant Opportunity (NGO) [for NJ LEAs], Section 1.9:

YEAR 1

Report	Quarterly Reporting Period *	Due Date________

1st Quarter	September 1, 2010 – November 30, 2010	December 15, 2010

2nd Quarter	September 1, 2010 – February 28, 2011	March 15, 2011

3rd Quarter	September 1, 2010 – May 31, 2011	June 16, 2011

Final	September 1, 2010 – August 31, 2011                   September 30, 2011

YEAR 2

Report		  Quarterly Reporting Period*		  	  Due Date________

1st Quarter	September 1, 2011 – November 30, 2011	December 15, 2011

2nd Quarter	September 1, 2011 – February 28, 2012	March 15, 2012

3rd Quarter	September 1, 2011 – May 31, 2012	June 16, 2012

Final	September 1, 2011 – August 31, 2012                   September 30, 2012

YEAR 3

Report	Quarterly Reporting Period *	Due Date________

1st Quarter	September 1, 2012 – November 30, 2012	December 15, 2012

2nd Quarter	September 1, 2012 – February 28, 2013	March 15, 2013

3rd Quarter	September 1, 2012 – May 31, 2013	June 16, 2013

Final	September 1, 2012 – August 31, 2013                  September 30, 2013

* Reporting is cumulative from the start date of each year.

Notice of Grant Opportunity (NGO) [for NJ LEAs], Section 2.2:

State Requirements and SEA Funded

State-required activities will be funded by the SIG state administrative funds. For the Leadership Academy, the LEA should allow for travel costs in the budget. LEAs must sign assurances agreeing to the following activities:

Peer Review

The Peer Review occurs in two stages. The first occurs prior to the LEA submission of the application. To fulfill the requirement of a peer review, NJDOE will use the services of a successful superintendent as the peer reviewer of each LEA application. This peer review will be consistent and equitable for all applicants. It will consist of written feedback to each LEA applicant who has the discretion for incorporation into the submitted SIG application. Stage two will occur after the award notification and during the pre-award contract review. This stage will be more intensive and involve direct contact between the LEA superintendent and the peer reviewer.

The NJDOE believes a focused, systemic action plan can help turn around struggling schools and districts. Conversely, the absence of an effective plan leads to a diffusion of effort, a lack of focus, and ineffective implementation of initiatives and reform efforts. Therefore, it is intention of the NJDOE to use the Peer Review to strengthen the LEA applications to increase the likelihood of success in implementation.

The Peer Review will help school leaders in school districts develop strong plans that are systemic and that focus efforts on improving the quality of instruction and raising student achievement. The Peer Review will ensure that every key action of the school is aligned with district goals and objectives. The long-term outcome of this reform initiative is to assist in increasing the district and school capacity to improve instruction and raise student achievement.

Leadership Academy

Research suggests that principals and superintendents have a greater impact on student learning than any other factor except the quality of classroom instruction. Principals can profoundly influence student achievement by working with teachers to shape a school environment that is conducive to learning; aligning instruction with a standards-based curriculum; organizing resources to improve classroom instruction and student learning; and making good decisions about hiring, professional learning, and other issues that influence the quality of teaching. Substantial and sustained professional development is necessary to refine and develop the skills that will assist the principal in effecting dramatic change in the level of student achievement. Working in conjunction with those cutting-edge institutions of higher education and other educational entities that are breaking the mold to support turnaround, and with transformational school leaders, the NJDOE will establish a leadership academy to train the SIG principals. This academy will start this summer by delivering a training during a three-week intensive program on such topics as effective use of curriculum and instructional tools, instructional leadership skills, fostering professional learning communities, motivating staff and students, and using data to inform management decisions. This professional-learning community will also serve as a resource to principals to problem-solve and share successful interventions. The academy will prepare the school-turnaround principal to leverage this unprecedented operational flexibility (including flexibility regarding staffing, calendars/time, and budgeting) in ways that have been proven to build a school culture that is focused on improving the academic achievement of its students, and, as the culture changes, to fill open positions in the school based on candidates’ qualifications. The principal will also be given the maximum amount of flexibility in federal, state, and local funding sources to enable the school to pursue evidence-based school improvement. The training sessions will be integrated with LEA superintendents to assure a shared vision and coherent implementation. The formal “networks” for both principals and superintendents will be reconvened throughout the year to ensure that the collaborative network is sustained. It is anticipated that the leadership academy will occur in August, 2010.

Network Turnaround Officer

The Network Turnaround Officer (NTO) will play a critical role in turning around struggling schools. As a facilitator of reform, the NTO will be responsible for initiating improvements in classroom instruction by helping to incorporate research-based practices to identify solutions to problems with student learning. In collaboration with the school principal, the NTO will set a clear pathway toward distributed leadership within the schools, working with a highly-capable team to build a cohesive, professional teaching culture. The NTO will also help the principal develop turnaround management skills. As an evaluator, the NTO will monitor the schools’ adherence to the intervention plan and tracking performance metrics, including academic achievement, against quantifiable plan objectives and assist the NJDOE in making decisions about the annual renewal of the SIG grant. The NTO will participate in the Leadership Academy along with the district and school staff.

NJDOE will conduct a nation-wide selection process to find candidates who are outstanding and highly skilled school leaders. NJDOE will develop an NTO Job Description and post notices regarding applications for the position. Once a pool of qualified candidates is collected, LEAs will select and hire an NTO from the state-developed list. The NTO contract with the LEA will be renewed on an annual basis, depending upon progress as determined by the LEA. The State will create LEA networks comprised of 3-5 schools, taking into account geographic factors, each school’s root causes of low performance, and school context. The LEA superintendents within networks will convene to determine the NTO selection. The state will act in an advisory capacity with regard to NTO placement. In some cases, all the schools will be located in one district, while in others, the NTO will serve schools in multiple districts and will be responsible for coordinating operations across the LEAs in which the schools reside. In these cases, New Jersey’s long history with shared services among LEAs will be a strong foundation on which to build. The NTO will support the cross-LEA relationships necessary to build a collaborative work group among the LEA superintendents and school leaders. The LEA superintendent(s) will evaluate the NTO on the basis of the school’s success in meeting its goals, the results of the state audit report, and the implementation fidelity of school-improvement interventions.

The NJDOE will fund the NTOs for the first year of the SIG grant. Thereafter, the LEA will be responsible to fund these services using their SIG grant funds.

External Evaluation

On an annual basis, the NJDOE will conduct an external implementation audit of curriculum, academic growth, school climate, teacher evaluations, and accompanying targeted professional development. The report will address all areas of the model implementation and explicitly report on progress against the quantifiable benchmarks of the intervention plan. These annual audits of each persistently-lowperforming school will include constructive feedback and recommendations for program improvements, as appropriate.

In the absence of sufficient progress or lack of implementation fidelity, the audit may include a recommendation for school closure or restart. The results of this audit will be reported publicly and will serve as part of the evaluation of the Network Turnaround Officer who is assigned to the school. These audits will be submitted to the LEA superintendent for review. A face-to-face meeting will occur with the NJDOE and each LEA superintendent to discuss the results and determine if refinement of the SIG plan for each of the served schools is necessary. The results will assist the NJDOE in annual SIG renewal decisions.

State Recommended and Funded by the LEA

Ten additional points will be awarded to the school applications that include SIG funding in their budgets for this state recommended optional activity. The expected cost is for training and coaching of teachers and materials. The LEA needs to allocate $60,000 per school for this activity. In the Project Description and Budget, clearly indicate if this activity is included in the NGO.

Curriculum and Assessment Spine

The Curriculum and Assessment Spine consists of exemplar units and lessons that embed the content and pedagogical routines necessary to change classroom practice and increase student achievement. Closely aligned with state content standards, this expanded set of exemplar lessons and units will be supported by a formative-assessment system that is designed to assist teachers in the customization of instruction to meet their students’ specific academic needs. A team of supervisors, content-focused instructional coaches and effective teacher leaders, assigned by the LEA, will assist teachers and school leaders in analyzing formative-assessment data, selecting customized comprehensive instructional interventions that meet the academic needs of individual students, and continuously monitoring student progress toward proficiency. This team of content-focused instructional leaders will support and maintain professional learning communities, and target and adapt professional development in response to specific teacher needs and the instructional demand of the content, in exemplar lessons throughout the school year. At its heart, this work will drive a data-based culture within the school and foster professional communities of practice. This focus on a coherent curriculum with regular opportunities for teachers to continuously improve their instruction has been demonstrated to have the most impact on student achievement. If the school will participate in the Curriculum and Assessment Spine, information should be included in the Project Description, Budget Narrative and Budget Detail.

Part I – Section F: The SEA must briefly describe the activities related to administration, evaluation, and technical assistance that the SEA plans to conduct with the State-level funds it has received from its School Improvement Grant.

The NJDOE intends to reserve 5% of the SIG funds for state-level administrative activities. The State funded activities include the following:

- Peer Review

- Leadership Academy

- Network Turnaround Officer

- External Evaluation

Detailed information about these activities are included in Part II of this application in Section 2: Project Guidelines.

SIG schools will also continue to have the opportunity to participate in the on-going technical assistance offered through the state system of support. These include the following workshops: data analysis, needs assessment, the annual NCLB conference, regular Title I sessions (Supplemental Educations Services, Accountability, Fiscal and Compliance) and the Effective Case Study Project.