Strengthening the Statewide System of Support

Process at a Glance

| Steps in Process | Products | Timeline | Deliverables to SEA |
| --- | --- | --- | --- |
| Step 1: CC-SEA agreement | Letter from CC to Chief | Day 1 |  |
| Step 2: SEA appoints self-assessment team | Letter from Chief to CC; Letter from CC to Team | Day 10 |  |
| Steps 3-5 in 2-day meeting with SEA self-assessment team and Comprehensive Center assistance team |  |  |  |
| Step 3: CC orients self-assessment team | Schedule for remaining steps; superintendents/principals to interview | Day 20 |  |
| Step 4: Self-Assessment team completes Inventory and submits key documents | Inventory and Key Documents | Day 20 |  |
| Step 5: CC conducts interviews with: a) self-assessment team; b) superintendents; c) principals | Interview Forms | Day 20 |  |
| Step 6: CC conducts interviews with: superintendents and principals | Interview Forms | Day 35 |  |
| Step 7: CC drafts Self-Assessment Report | Draft of Self-Assessment Report | Day 55 |  |
| Step 8: SEA convenes SSOS personnel for day to review Report; CC facilitates | Critique and consensus by SSOS personnel | Day 65 |  |
| Step 9: CC revises Report | Final Self-Assessment Report | Day 70 | SSOS Self-Assessment Report |
| Step 10: Self-assessment team with CC develops Plan to Strengthen SSOS | Plan to Strengthen the SSOS | Day 80 | Plan to Strengthen the SSOS |
| Step 11: The SEA self-assessment team and Comprehensive Center staff submit the final SSOS Self-Assessment Report and Plan to the Chief State School Officer and meet with the CSSO to discuss it and plan next steps authorized by the CSSO. | Revised plan as approved by CSSO and next steps | Day 90 | Revised Plan as approved by CCSSO and next steps |
| Step 12: Plan is implemented; CC assists with TA and monitoring | Progress Reports |  |  |

Time Commitments for SEA

- Self-Assessment Team (5 to 9 senior personnel with responsibility for SSOS, appointed by Chief)

  - Completion of Inventory, Interview, and Submission of Key Documents – 12 hours (2 days of 6 hours)

  - Participation in Day of Review of Report – 6 hours on 1 day

  - Completion of Plan to Strengthen the SSOS – 6 hours on 1 day

  - Meeting with Chief to Review and Amend Plan – 2 hours on 1 day

- SSOS Personnel (including SEA staff involved with SSOS and field staff, partners)

  - Participation in Day of Review of Report – 6 hours on 1 day