12 Steps to Strengthen the Statewide System of Support

Step 1:  	Contact is made between the SEA and the Comprehensive Center and an agreement to engage in the assistance process is reached. See Letter of Introduction to chief state school officer (CSSO).

Within 10 days after agreement is reached:

Step 2:  	The CSSO appoints a self-assessment team consisting of 5 to 9 key personnel with responsibility for major components of the statewide system of support. See Welcome Letter.

Steps 3-5 are completed in a 2-day meeting of the SEA self-assessment Team facilitated by the Comprehensive Center. Within 10 days after CCSSO appoints the SEA self-assessment team:

Step 3:  	The Comprehensive Center orients the SEA self-assessment team to the Framework for an Effective Statewide System of Support and the SSOS Assessment and Planning Process.

Step 4:  	The SEA self-assessment team reviews Strengthening the Statewide System of Support, completes the SSOS Self-Assessment Inventory, and assembles documents requested prior to the interview.

Step 5:  	The Comprehensive Center staff interviews the SEA self-assessment team, completing the SSOS Self-Assessment Interview Form.

Within 15 days after the Self-Assessment Interview:

Step 6: 	At the SEA’s discretion, the Comprehensive Center staff interviews LEA representatives, selected by the SEA, to obtain a customer perspective related to SSOS services currently provided.

Within 20 days after the field interviews:

Step 7:  	The Comprehensive Center staff uses the data collected on the SSOS Self-Assessment Inventory, key documents, SSOS Self-Assessment Interview Form, and interviews with LEAs to prepare an analysis report (SSOS Self-Assessment Report) intended to inform a plan for strengthening the SSOS.  This report contains sufficient descriptive information to illustrate the sections of the framework.

Within 10 days after notification by the Comprehensive Center that the analysis report is ready to be presented:

Step 8:  	The SEA convenes a wider group of personnel and partners already involved in the statewide system of support to discuss, comment on, and amend, as necessary, the content of the SSOS Self-Assessment Report.  (Note:  SEA should plan for this session to last 1 day)

Within 5 days after the meeting of the large group to discuss the original report:

Step 9:  	The Comprehensive Center staff revises the SSOS Self-Assessment Report based on the feedback from the wider group.

Within 10 days after notification by Comprehensive Center that SSOS Self-Assessment Report has been revised:

Step 10:  	The Comprehensive Center staff meets with the SEA self-assessment team for a day to identify strengths and weaknesses from the report, as revised, and develop a Plan to Strengthen the Statewide System of Support, including a monitoring plan.

Within 10 days after Completion of the Plan to Strengthen the Statewide System of Support:

Step 11: 	Plan and Report are presented to the chief state school officer, revised, approved.

Time frame for continuing assistance to be laid out in Plan to Strengthen the Statewide System of Support.

Step 12: 	The Comprehensive Center staff continues to provide assistance to the SEA related to plan implementation, monitoring progress, and evaluation as specified in the plan.